## Project Plan
Phase / Category | Description | Status | Owner
PHASE 1 — PROJECT SETUP & DATA ACQUISITION
Data Acquisition | Source a recipe dataset (e.g., Recipe1M, Kaggle recipe dataset, or Spoonacular API dump) | Complete | Ken
Data Acquisition | Define ingredient taxonomy — map ingredient class labels between the image dataset and recipe dataset | Complete | Lily
Data Prep | Annotate / convert image annotations to YOLO format (class_id, x_center, y_center, w, h) | Complete | Payton
Data Prep | Clean recipe dataset — normalize ingredient names, remove duplicates, handle missing fields | Complete | Payton
PHASE 2 — EXPLORATORY DATA ANALYSIS (EDA)
Image EDA | Report dataset stats: total images, images per class, train/val/test split counts | Complete | Lily
Image EDA | Visualize sample images per ingredient class (grid of examples) | Complete | Lily
Image EDA | Plot class distribution bar chart — identify imbalanced classes | Complete | Lily
Image EDA | Analyze image properties: resolution histogram, aspect ratio distribution, channel statistics | Complete | Lily
Image EDA | Identify and display outlier / noisy images; document cleaning decisions | Complete | Lily
Recipe EDA | Summarize recipe dataset: total recipes, avg ingredients per recipe, missing value analysis | Complete | Ken
Recipe EDA | Plot top-N most common ingredients (bar chart) and ingredient co-occurrence heatmap | Complete | Ken
Recipe EDA | Visualize recipe complexity distribution (violin / box plot of ingredient counts) | Complete | Ken
Recipe EDA | Bivariate analysis: cuisine type vs. ingredient frequency, recipe rating vs. complexity | Complete | Ken
PHASE 3 — PROBLEM 1: INGREDIENT DETECTION (OBJECT DETECTION)
Model 1A — YOLOv8 | Set up Ultralytics YOLOv8 pipeline; configure data.yaml with class names and paths | In Progress | Payton | 01_Data_Prep_Merge.ipynb
Model 1A — YOLOv8 | Train YOLOv8n/s model with baseline hyperparameters; log training curves | In Progress | Payton | 02b_Colab_Baseline_Training.ipynb
Model 1A — YOLOv8 | Hyperparameter tuning: experiment with learning rate, augmentation, image size, epochs | In Progress | Payton | 02c_Colab_Hyperparameter_Tuning.ipynb
Model 1A — YOLOv8 | Evaluate on test set — generate mAP@50, mAP@50:95, precision, recall, per-class AP | In Progress | Payton | 02d_Colab_Final_Evaluation.ipynb
Model 1B — Faster R-CNN | Implement Faster R-CNN (torchvision) as the challenger model with same dataset splits | Complete | Lily
Model 1B — Faster R-CNN | Train Faster R-CNN; experiment with backbone (ResNet-50 vs. MobileNet) | In Progress | Lily
Model 1B — Faster R-CNN | Evaluate on test set — same metrics as YOLOv8 for fair comparison | In Progress | Lily
Comparison | Build comparison table & charts: mAP, inference speed (FPS), model size, per-class breakdown
Comparison | Discuss pros/cons of each architecture w.r.t. the ingredient detection task
PHASE 4 — PROBLEM 2: RECIPE MATCHING / RECOMMENDATION
Feature Engineering | Build ingredient-to-recipe index: for each recipe, store a set of required ingredients | Complete | Ken
Model 2A — Content-Based | Implement set-similarity matching (Jaccard / cosine on binary ingredient vectors) to rank recipes | Complete | Ken
Model 2A — Content-Based | Evaluate with metrics: hit rate, mean reciprocal rank, coverage of detected ingredients | Complete | Ken
Model 2B — Embedding NN | Train a neural embedding model (e.g., ingredient2vec or a small MLP/Transformer) to learn ingredient-recipe similarity
Model 2B — Embedding NN | Evaluate with same metrics as Model 2A for fair comparison
Comparison | Build comparison table & charts for recipe matching models
Integration | Wire end-to-end pipeline: image → YOLO detection → extracted ingredients → recipe recommender → ranked results
PHASE 5 — MODEL OPERATIONS (MLOps)
Architecture | Design and diagram the deployment architecture (e.g., FastAPI backend + Streamlit/Gradio frontend) |  | Payton
Serving | Export best YOLO model to ONNX/TorchScript; wrap in a REST API endpoint |  | Payton
Serving | Build a simple demo UI: user uploads image → shows detected ingredients → shows matched recipes |  | Lily
Maintenance Plan | Document model retraining strategy: triggers, data drift monitoring, versioning (MLflow or DVC) |  | Lily
PHASE 6 — REPORT & PRESENTATION
Abstract | Write collaborative abstract summarizing problem, approach, and key results | In Progress | Ken
Report — EDA | Compile EDA section with all visualizations and analysis narrative | Complete | Ken
Report — Models | Write up model training, evaluation, and comparison sections for both problems | In Progress | Ken
Report — MLOps | Write deployment architecture and maintenance plan section | In Progress | Ken
Report — Conclusion | Write conclusion: key findings, limitations, future work, references | In Progress | Ken
Presentation | Create slide deck (~20 slides); assign ~5 min speaking per member